## Slide 1: 2023/24 Finance Committee Work Plan
DRAFT
June 19, 2023

## Slide 2: 2023/24 Work Plan: Draft Areas of Focus
Potential Area of Focus | Deliverable / Objective | Start | End | FC Owner | Votes Rec'd | Weighted Average
Sustainable revenue growth | Encourage Select Board (SB), School Committees (SCs), others to develop new sources of sustainable growth | Jun-23 | 24-May |  | 9 (7) | 3.20 (1.73)
Capital spend and planning | Provide input on Tier 1 and Tier 2 capital items Ask for integrated five-year plans | Jun-23 | 23-Dec |  | 9 | 2.07
Outreach/communications on FC | Develop communications strategy ad tactics Proactively communicate major FC information & decisions to residents | Jun-23 | 24-May |  | 9 | 1.67
CPS strategic plan | Ask School Committees (SCs) for periodic updates Encourage FY 25 budget requests be "connected" to strategic plan | 23-Jul | 24-May |  | 6 (5) | 1.47 (0.8)
Town strategic plan | Encourage Town to develop robust five-year strategic plan | Jul-23 | TBD |  | 6 | 1.13
Middle School Building project | Keep abreast of budget vs actual costs and budget impact of committee decisions | 23-Jul | 24-May |  | 5 (4) | 2.13 (0.8)
2229 Main Street | Encourage revenue-oriented approaches to site development/use Provide input to draft recommendations | TBD | TBD |  | 5 | 0.80
Recreation Department strategy | Understand budget impacts of this plan and incorporate those impacts into our cap plan forecast | TBD | TBD |  | 4 | 0.80
250th Anniversary celebrations | Encourage use of private fund raising such that Town is not required to appropriate funds in FYs 2025 nor 2026 If necessary, estimate impact to taxpayers in 2024 Annual Report | Jul-23 | 24-May |  | 4 | 0.40
Votes of 10 pts more excluded and results shown in (X.XX)

## Slide 3: 2023/24 Work Plan: Others
Potential Area of Focus | Deliverable / Objective | Start | End | FC Owner | Votes Rec'd | Weighted Average
Can be included in existing areas of focus and work product |  |  |  |  |  | 
CPS union contracts | Incorporate several potential scenarios into five-year cost estimates Incorporate potential scenarios into FC Annual Report | 23-Sep | 23-Apr |  | 3 | 0.53
Housing Development | Revenue opportunities |  |  |  | 2 (1) | 1.13 (0.13)
Improve Guideline process | Permit time to make changes at the end? |  |  |  | 1 | 0.40
Zoning changes | Advise voters on potential tax impacts, pos & neg, of major zoning changes i.e. MBTA Zoning Overlay District |  |  |  | 1 | 0.33
Improve Annual report | Show total impact of articles on taxes |  |  |  | 1 | 0.13
Others? |  |  |  |  |  | 
Benefit spending | Encourage Town and Schools to separately track benefit spending for Town and non-teacher School employees | 23-Jul | TBD |  | 3 | 0.33
Incorporate use of IRR for capital projects | Apply IRR model to our recommendations for discretionary capex in Capital Plans and Sustainability project, ie solar, or hvac system replacement |  |  |  | 1 | 0.13
Do not include in 2023/24 Work Plan? |  |  |  |  |  | 
Sustainability | Develop FC position/principles on sustainability Use when making recommendations | TBD | 24-May |  | 2 | 0.33
Waste water treatment | Keep abreast of proposed warrant article upgrade the waste water treatment plant |  |  |  | 1 | 0.33
Votes of 10 pts more excluded and results shown in (X.XX)

## Slide 4: Next Steps